Niger Delta Gas Infrastructure Expansion (NDGIE) Project

PROJECT EXECUTION STRATEGY — ASSESS (EARLY) STAGE

Owner: Nigerian National Petroleum Company Ltd (NNPCL)
Operator: DeltaGas JV (NNPCL 60%, Seaway Energy 25%, PetroNova 15%)
Date: October 2025
Version: Rev 0

――――――――――――――――――――――――――――――――――――――――

## Revision History

| Rev. | Date | Description of Change | Prepared By | Reviewed By | Approved By |
| --- | --- | --- | --- | --- | --- |
| 0 | Oct 2025 | Initial Issue (Assess Stage Draft) | PMC Team | Project Director | Steering Committee |
| 1 | TBD | Final for Review | PMC Team | NNPCL Representative | DeltaGas JV Board |

Table of Contents

Revision History	2

1. Executive Summary	5

Lifecycle Roadmap	5

2. Project Background and Objectives	5

3. Scope Definition	5

Integrated Block Flow Diagram	6

4. Execution Philosophy and Strategy	6

Execution Hierarchy (Vision → Field)	7

5. Governance and Assurance (Overview)	7

Governance Org Chart	7

6. Contracting and Procurement Strategy	8

Contracting Strategy Flow	8

7. HSSE and Sustainability	8

Bowtie (Major Accident Hazard) – Placeholder	9

8. Risk & Opportunity Management	9

Risk Heat Map	10

9. Security Management Plan	10

10. Schedule and Milestones	10

High-level Gantt Timeline	11

11. Cost Estimation & Project Controls	11

12. Change Management	12

Change Workflow	12

13. Quality Assurance & Technical Integrity	12

14. Stakeholder Engagement Plan	12

Stakeholder Influence–Interest Matrix	13

15. Information Management & Communication	13

16. Transition to Define (FEED) Stage	13

Appendices	14

A. Detailed Risk Register (Top 20)	14

B. Assess-Stage Deliverables List	15

C. Glossary & Abbreviations	15

## 1. Executive Summary

1.1 Purpose and Strategic Intent

The Niger Delta Gas Infrastructure Expansion (NDGIE) program is a national-scale initiative to monetize stranded associated and non-associated gas, cut routine flaring, and deliver reliable domestic energy to Nigeria’s industrial corridors. In the Assess Stage, NDGIE will confirm technical and commercial viability, define the execution and contracting model, de-risk environmental and stakeholder interfaces, and secure Gate-2 approval to mobilize FEED in Q3 2026.

The project directly supports the Decade of Gas and the Energy Transition Plan (ETP 2060) by converting otherwise flared gas into pipeline-spec gas for industry and power, as well as LPG/NGL and condensate products for local markets

1.2 Strategic Rationale and Value Proposition

- Decarbonization & Compliance: Monetizes gas currently flared, avoiding ~4.0 MtCO₂e/year and aligning with IFC/FMEnv expectations.

- Industrial Growth & Reliability: Delivers up to 500 MW of firm power to industrial hubs, improving grid stability and enabling manufacturing/logistics expansion.

- Petrochemical Feedstock & Cooking Fuel: Supplies LPG/NGL and stabilized condensate to domestic markets, supporting petrochem/value-add chains and cleaner household fuels.

- Local Content & Jobs: Target ≥60% Nigerian Content by man-hours and ≥40% by value; creates 3,000+ direct and 10,000+ indirect jobs with structured skills transfer.

### Lifecycle Roadmap

## 2. Project Background and Objectives

Nigeria’s Decade of Gas and the Energy Transition Plan (ETP 2060) set the context for monetizing gas, reducing flaring, and supporting industrialization. NDGIE responds to this mandate by integrating gas gathering, processing, power generation, and export infrastructure. The JV structure (NNPCL 60%, Seaway Energy 25%, PetroNova 15%) aligns national priorities with private investment. Objectives include safe delivery, schedule certainty, competitive cost, and robust environmental and social stewardship across sensitive wetland and community corridors.

▣ Project Objectives

1) Monetize 1.2 BCF/D of gas for domestic and export markets; 2) Deliver 500 MW embedded power for industrial clusters; 3) Achieve Train 8 expansion; 4) Maximize Nigerian content (≥60%); 5) Meet IFC and Nigerian ESIA standards; 6) De-risk interfaces via a PMC-led, multi-EPC model.

## 3. Scope Definition

| Component | Description | Key Quantities |
| --- | --- | --- |
| Gas Gathering | 350 km, 36” trunkline interlinking six hubs; pigging stations; block valves | 1.2 BCF/D throughput |
| Processing & Fractionation | Central Gas Complex (inlet separation, dehydration, NGL recovery, fractionation) | 1.2 BCF/D; C2/C3+ products |
| Power Generation | Two 250 MW open/combined-cycle gas turbines; black-start and redundancy | 500 MW total |
| Export | Bonny Terminal revamp, jetty upgrades, new LNG Train 8 | ~6 mtpa incremental |
| Utilities & Infrastructure | Eight compressor stations; 40 km of 132 kV lines; laydown areas and camps | 8 stations; 40 km |

Scope boundaries (battery limits) and interfaces are explicitly defined to avoid overlap between EPC packages. Wetland crossings will employ HDD where feasible; pre-assembly and modularization will reduce field exposure. Tie-ins to existing assets will be planned during low-demand windows and aligned with stakeholder shutdown calendars.

### Integrated Block Flow Diagram

## 4. Execution Philosophy and Strategy

The project adopts a PMC-led, multi-EPC model to enable competitive tension and clear accountability. A data-centric engineering approach underpins design maturity, with model-based reviews, clash detection, and constructability assessments held at each maturity checkpoint. Modularization of skids (dehydration, compression, utility racks) reduces workfront congestion in swamp terrain and shortens the critical path. Early works (temporary access, logistics bases, power and water) are front-loaded to de-risk construction mobilization. Commissioning follows a systemization strategy aligned with subsystem MC/SC handovers and punch categorization (A/B/C).

▣ Key Principles

• Goal Zero HSSE;

• Single-source-of-truth data;

• Robust interface management;

• Early works & modularization;

• Predictable commissioning & handover.

### Execution Hierarchy (Vision → Field)

## 5. Governance and Assurance (Overview)

Governance operates at three tiers: (1) Steering Committee for strategy and approvals; (2) Project Management Committee for tactical alignment; (3) PMC-led execution teams for day-to-day delivery. Technical Assurance embeds independent reviews at concept selection, FEED readiness, HAZID/ENVID close-out, and contracting milestones. Escalation thresholds for change and claims are codified in the PEP and Contracting Plan.

### Governance Org Chart

## 6. Contracting and Procurement Strategy

Contract packaging is structured to reduce interfaces while preserving competition: Package A (Pipeline LSTK), Package B (Processing EPC), Package C (Power & Utilities EPC), and a reimbursable PMC. Selection is based on capability, Nigerian content, HSE performance, and financial strength. Long-lead items (compressors, turbines, cryogenic exchangers) are pre-identified; technical prequalification begins during Assess to compress FEED-to-EPC transition. E-procurement supports transparent bidding and vendor development.

| Package | Scope | Contract Type | Tender Launch (Indicative) |
| --- | --- | --- | --- |
| A | 350 km 36” trunkline incl. stations & HDD crossings | LSTK | Q3 2026 |
| B | Gas Processing Complex incl. utilities & offsites | EPC | Q4 2026 |
| C | Power Plants (2x250 MW) & 132 kV grid works | EPC | Q1 2027 |
| PMC | Integrated Project Management Consultancy | Reimbursable w/ KPIs | Q1 2026 |

▣ Local Content Plan

Target ≥60% Nigerian content via local fabrication yards (spools, pipe supports), training programs, and vendor qualification. Adopt ‘make where feasible, import where necessary’ to balance cost and schedule.

### Contracting Strategy Flow

## 7. HSSE and Sustainability

HSSE commitment is codified through project-specific Lifesaving Rules, permit-to-work discipline, and leadership site engagement (MSE). The ESIA roadmap aligns with Nigerian EIA Act and IFC Performance Standards: scoping, baseline surveys, impact assessment, and management plans (EMP, SMP, WMP, BMP). Sustainability priorities include flare reduction, energy efficiency, water stewardship, and biodiversity protection in mangrove/wetland habitats.

HSSE ‘Golden Rules’: Comply with procedures; Intervene on unsafe acts; Respect the environment.

### Bowtie (Major Accident Hazard) – Placeholder

⬚⬚⬚ EDITABLE GRAPHIC PLACEHOLDER ⬚⬚⬚

Loss of containment at compressor station – barriers & escalation controls

## 8. Risk & Opportunity Management

Risk management follows ISO 31000. A living risk register captures threats and opportunities with owners, actions, and due dates. Quantitative risk analysis (QRA) informs contingency. Opportunities include modularization savings, local fabrication, and early power revenues.

| Risk ID | Description | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-001 | ROW acquisition delays | High | High | Community MoUs; compensation framework; early survey permits |
| R-002 | ESIA approval delay | Medium | High | NESREA/NUPRC pre-engagement; complete baseline early |
| R-003 | Security incidents (Niger Delta) | High | High | 24/7 marine patrols; vetted escorts; journey management |
| R-004 | Cost escalation & forex risk | High | Medium | Benchmarking; VE; forex hedging; framework agreements |
| R-005 | Contractor performance variance | Medium | High | Performance KPIs; earned value; incentive/LDs structure |

### Risk Heat Map

## 9. Security Management Plan

Security is risk-based and community-sensitive. Measures include vetted security providers, coordination with civil authorities, monitored marine routes, and geofenced journey management. A grievance mechanism supports community relations, minimizing disruptions to ROW works.

## 10. Schedule and Milestones

The Level-1 schedule defines phase gates and critical path: Concept Selection (Q2 2026), FEED kickoff (Q3 2026), EPC tendering (Q1 2027), FID (Q4 2027), Construction start (Q1 2028), Mechanical Completion (Q4 2030), and RFSU (Q2 2031). Front-end activities focus on early works, permitting, and long-lead procurement to compress overall duration.

| Milestone | Start Date | Finish Date | Phase |
| --- | --- | --- | --- |
| Concept Selection Approved | Q3 2025 | Q2 2026 | Assess |
| FEED Kick-off |  | Q3 2026 | Define |
| EPC Tendering | Q4 2026 | Q1 2027 | Define |
| FID | Q2 2027 | Q4 2027 | Define |
| Procurement of LLI | Q1 2028 | Q3 2028 | Execute |
| Construction | Q2 2028 | Q4 2030 | Execute |
| Mechanical Completion |  | Q4 2030 | Execute |
| Commissioning & RFSU | Q1 2031 | Q2 2031 | Operate |

### High-level Gantt Timeline

## 11. Cost Estimation & Project Controls

A Class 4 estimate will be developed using analogous benchmarks and quantity-based factored models. Cost breakdown structure (CBS) aligns with WBS and contracts. Contingency is based on risk analysis and maturity. Project Controls integrates cost, schedule, and risk using EVMS to track CPI/SPI and forecast EAC.

| CBS Level | Element | Basis | Notes |
| --- | --- | --- | --- |
| L1 | Pipeline | Benchmark length/diameter factors | Includes HDD premiums; swamp logistics |
| L1 | Processing Complex | Major equipment + installation factors | Early modularization uplift then site reduction |
| L1 | Power Plants | OEM budgetary quotes | Balance-of-plant factored costs |
| L1 | Export & Utilities | Historical norms | Jetty/terminal revamp allowances |

▣ Controls Toolkit

• EVMS (CPI/SPI);

• Change control workflow;

• Risk-adjusted forecast;

• Monthly cost/schedule report;

• Dashboard KPIs.

## 12. Change Management

Change is controlled through a single intake (PCR), impact assessment (cost/schedule/HSSE), and approval thresholds (PMC, PMT, Steering Committee). Trends are tracked to anticipate budget movements. Contract changes follow predefined clauses for variations and claims.

### Change Workflow

## 13. Quality Assurance & Technical Integrity

Quality aligns with ISO 9001. ITPs define hold/witness points for critical activities (welding, NDT, coatings, hydrotests). Vendor surveillance ensures equipment conformity. Technical integrity checks verify design safeguards, relief systems, and operability before MC/SC.

| Discipline | Key QA Controls | Assurance Evidence |
| --- | --- | --- |
| Pipeline | WPS/PQR, weld maps, RT/UT/PAUT, coating holiday tests | ITPs, NCR logs, hydrotest packs |
| Process Plant | Equipment FAT/SAT, loop checks, calibration | QC dossiers, punch lists |
| Power | OEM acceptance tests, performance runs | OEM certificates, run logs |

## 14. Stakeholder Engagement Plan

Stakeholders include NUPRC/NESREA, state/local governments, host communities, partners, contractors, and financiers. A mapping exercise ranks influence and interest, informing engagement tactics: MoUs, grievance redress, capacity building, and transparent communication.

| Category | Stakeholder | Interest | Influence | Strategy |
| --- | --- | --- | --- | --- |
| Regulatory | NUPRC, NESREA | High | High | Permit tracker; early reviews |
| Community | Host/Transit communities | High | Medium | MoUs; local hiring; CSR projects |
| Partners | Seaway, PetroNova | High | High | Weekly JV reviews; clear RACI |
| Contractors | PMC/EPCs | Medium | High | Interface protocols; KPIs |
| Financial | ECAs/banks | High | Medium | Term sheets; ESG reporting |

### Stakeholder Influence–Interest Matrix

## 15. Information Management & Communication

A cloud-based EDMS governs document numbering, revisions, and transmittals. Communication follows a RACI-informed cadence: daily site briefs, weekly progress meetings, monthly Steering reviews, and quarterly assurance. Data governance ensures tag consistency, 3D model versioning, and cybersecurity for shared environments.

## 16. Transition to Define (FEED) Stage

FEED entry requires Concept Selection approval, BoD maturity, Class 4 estimate/schedule, ESIA scoping approval, and an endorsed contracting plan. A readiness checklist assigns deliverable owners and due dates, with a Gate-2 pack prepared for Steering endorsement.

| Gate-2 Item | Owner | Status |
| --- | --- | --- |
| Concept Selection Report | PMC | In progress |
| Basis of Design (BoD) | Engineering | Drafting |
| Class 4 Cost Estimate | Estimating | Benchmarking |
| L1 Schedule | Planning | Logic developed |
| ESIA Scoping Approval | HSSE | Engaging regulators |
| Contracting Strategy | Contracts | Draft ready |

## Appendices

### A. Detailed Risk Register (Top 20)

| ID | Risk Description | Category | Impact | Likelihood | Risk Rating | Mitigation Measures |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Delay in Right-of-Way acquisition across swamps | Land & Community | High | Likely | High | Early community engagement, alternative routing studies, secure government support |
| R2 | Security threats in the Niger Delta region | Security | High | Likely | High | 24/7 marine and ground patrols, MOU with local vigilante groups, embed security advisor |
| R3 | Interface misalignment between EPC packages | Execution | High | Possible | Medium-High | Strong PMC coordination, interface registers, 4D schedule integration |
| R4 | Gas feedstock shortfall from producing hubs | Supply/Technical | High | Unlikely | Medium | Diversify gas sources, tie-in phased commissioning, contractual production guarantees |
| R5 | Environmental impact during pipeline construction | Environmental | Medium | Likely | Medium | Full EIA compliance, HDD under water crossings, environmental monitoring plan |
| R6 | Cost overrun due to inflation or scope creep | Commercial | High | Possible | Medium-High | Fixed-price EPC contracts, strong cost control governance |
| R7 | Low local content performance by contractors | Regulatory | Medium | Possible | Medium | Enforce NCMB regulations, set KPIs in contract, embed local compliance reporting |
| R8 | Delay in Regulator approvals (e.g., NUPRC, NESREA) | Regulatory | Medium | Possible | Medium | Pre-submission engagement, regulator workshops, early documentation readiness |
| R9 | Power plant interconnection delays (132 kV line) | Technical | Medium | Unlikely | Low | Parallel permit application, engage grid operator early, phased energization plan |
| R10 | LNG terminal tie-in interface risks | Infrastructure | High | Unlikely | Medium | Detailed interface schedule, dedicated tie-in coordination team |

### B. Assess-Stage Deliverables List

| Deliverable | Owner | Due |
| --- | --- | --- |
| Concept Selection Report | PMC | Q2 2026 |
| BoD | PMC/Engineering | Q2 2026 |
| Class 4 Estimate | Estimating | Q2 2026 |
| L1 Schedule | Planning | Q2 2026 |
| HSSE Scoping Report | HSSE | Q2 2026 |
| Stakeholder Plan | CSR & Legal | Q2 2026 |
| FID Readiness Roadmap | Project Controls | Q2 2026 |

### C. Glossary & Abbreviations

BoD – Basis of Design; CSR – Corporate Social Responsibility; EDMS – Electronic Document Management System; ENVID – Environmental Identification; EPC – Engineering, Procurement, and Construction; ESIA – Environmental and Social Impact Assessment; FEED – Front-End Engineering Design; FID – Final Investment Decision; HAZID – Hazard Identification; HDD – Horizontal Directional Drilling; HSSE – Health, Safety, Security, Environment; IFC – International Finance Corporation; JV – Joint Venture; LSTK – Lump Sum Turnkey; NESREA – National Environmental Standards and Regulations Enforcement Agency; NUPRC – Nigerian Upstream Petroleum Regulatory Commission; PMC – Project Management Consultancy; ROW – Right of Way; RFSU – Ready for Start-Up; WBS – Work Breakdown Structure.