# MONTHLY PROJECT PROGRESS REPORT

ENGINEERING, PROCUREMENT AND CONSTRUCTION OF A FIFTY- HOME APARTMENT COMPLEX

Client: Shark Inc. Real Estate Division

Reporting Month: October 2025

Table of Contents

1. Executive Summary	4

2. Project Overview	5

Project Background and Objectives	5

Scope Summary	5

3. Progress Summary	6

4. Cost & Schedule Performance	7

5. Quality, Health, Safety & Environment (QHSE)	8

6. Risk Management	10

7. Key Issues and Concerns	11

8. Upcoming Milestones / Next Period Plan	12

9. Appendices	13

# 1. Executive Summary

The Engineering, Procurement, and Construction (EPC) of the Fifty-Home Apartment Complex continues to record steady progress across all project phases — Engineering, Procurement, and Construction. The reporting month of October 2025 witnessed notable advancements in both design finalization and on-site activities, despite minor schedule slippages linked to supply chain delays and weather-related disruptions.

Overall physical progress currently stands at 45%, with the Engineering phase substantially completed at 70%, Procurement at 60%, and Construction at 30%. Key deliverables achieved this period include completion of structural works for Blocks A and B, approval of 80% of shop drawings, and successful factory acceptance tests (FAT) for major electrical panels and HVAC equipment.

| KPI | Status | Current Value | Remarks |
| --- | --- | --- | --- |
| Cost Performance Index (CPI) | 🟢 | 1.02 | On Budget |
| Schedule Performance Index (SPI) | 🟡 | 0.94 | Slight Delay |
| Safety Performance | 🟢 | Zero LTI | Safe Work Month |
| Quality Compliance | 🟢 | 98% | Acceptable Range |

The project remains within budget, with a Cost Performance Index (CPI) of 1.02, indicating efficient cost utilization, while the Schedule Performance Index (SPI) of 0.94 reflects a slight delay relative to the baseline schedule. Mitigation measures have been initiated to recover the schedule through resource reallocation, extended work shifts, and improved logistics coordination.

Quality performance remains satisfactory, with a compliance rate of 98% across inspected works. Minor non-conformances identified during routine inspections were immediately rectified. Safety performance continues to be commendable — the project has maintained zero Lost Time Incidents (LTI) since inception, supported by proactive toolbox talks, hazard identification campaigns, and rigorous permit-to-work enforcement.

Procurement activities are progressing well, with most long-lead items already ordered and several critical materials delivered to site. Some delays were experienced in façade panel fabrication due to vendor backlog, but alternative sourcing and expediting efforts are underway.

Risk management efforts have focused on mitigating the top risks identified: (1) delayed façade panel delivery, (2) prolonged rainfall affecting civil works, and (3) manpower shortages for electrical installation. These are being closely monitored with weekly progress reviews and vendor performance follow-ups.

Looking ahead, the next reporting period will focus on completing MEP rough-ins for Blocks A–D, installation of HVAC equipment, and mobilization of the finishing contractor. With continued attention to schedule optimization and field productivity, the project remains poised to achieve substantial completion within the approved timeline.

# 2. Project Overview

## Project Background and Objectives

The Engineering, Procurement, and Construction (EPC) of the Fifty-Home Apartment Complex is a strategic residential development project initiated by Shark Inc. Real Estate Division to address the growing demand for modern, high-quality housing within the Lekki–Ajah axis of Lagos, Nigeria. The development consists of fifty contemporary apartment units spread across multiple blocks, supported by associated infrastructure including internal road networks, stormwater drainage systems, water supply and storage facilities, power distribution networks, and sewage treatment systems.

The project scope encompasses the full EPC lifecycle — from design engineering and detailed modeling through procurement of all major materials and equipment, to the construction, installation, and commissioning of complete residential units and supporting utilities. This integrated delivery approach ensures technical efficiency, cost control, and adherence to quality and safety standards.

The primary objective of the project is to deliver high-quality, energy-efficient, and sustainable apartment units equipped with modern mechanical and electrical amenities, smart metering systems, and eco-friendly lighting solutions. The development aims to create a benchmark for residential living by combining functionality, comfort, and aesthetics while optimizing long-term maintenance and operational performance.

Upon completion, the project will provide housing for over 200 residents, create significant employment opportunities during its execution phase, and contribute to the ongoing urban development initiatives of Shark Inc. within Lagos State. The project is planned to be executed within the approved schedule and budget, ensuring timely delivery, zero harm, and full compliance with local regulatory requirements.

## Scope Summary

The project scope covers the complete Engineering, Procurement, and Construction (EPC) phases required to deliver a fully functional fifty-home residential complex that meets design intent, quality standards, and client expectations. The summary of scope under each phase is as follows:

- Engineering:
This phase entails all civil, structural, mechanical, electrical, and architectural design deliverables necessary to translate the project concept into an executable plan. Key activities include detailed design development, preparation of construction drawings, model reviews, and coordination across all disciplines to ensure constructability, code compliance, and alignment with client specifications. Engineering deliverables also encompass as-built documentation, design change management, and interface coordination among consultants and contractors.

- Procurement:
This phase involves strategic sourcing, purchasing, and logistics management of all project materials, equipment, and long-lead items. Major procurement packages include HVAC systems, electrical distribution panels, finishing materials, sanitary fittings, and prefabricated façade elements. Procurement efforts focus on ensuring timely vendor engagement, quality assurance through factory acceptance tests (FAT), and efficient delivery to site in alignment with the construction sequence.

- Construction:
The construction phase covers all site execution works, from foundation preparation to final finishing. It includes substructure and superstructure construction, masonry and roofing works, mechanical–electrical–plumbing (MEP) installation, façade works, internal and external finishes, and commissioning activities. Emphasis is placed on maintaining safe work practices, adherence to quality control procedures, and schedule optimization to ensure timely project delivery.

# 3. Progress Summary

Overall project physical progress as at the end of October 2025 stands at approximately 45%, showing steady advancement across all project disciplines. The project continues to maintain momentum in both engineering and procurement activities, while construction works are progressing on multiple fronts within the site.

Phase-Wise Progress Overview

| Phase | Progress (%) | Remarks |
| --- | --- | --- |
| Engineering | 70% | Detailed design packages for civil, structural, and MEP disciplines have been completed and approved. Remaining deliverables include final as-built drawings and minor design revisions arising from site interface clarifications. |
| Procurement | 60% | Most major purchase orders have been issued. Long-lead items such as HVAC systems and electrical panels have undergone successful Factory Acceptance Tests (FAT). Logistics planning for delivery to site is ongoing to support the construction sequence. |
| Construction | 30% | Civil and structural works for Blocks A and B have reached advanced stages, with foundation and superstructure works substantially completed. MEP rough-in activities are ongoing across multiple blocks, while façade and finishing mobilization are being planned for the next period. |
| Overall Progress | 45% | On track with key project objectives, though affected slightly by weather-related disruptions and minor vendor delays. Recovery plans have been initiated through schedule optimization and additional work shifts. |

Highlights of the Month

- Completion of structural works for Blocks A and B.

- Approval of 80% of construction drawings and shop drawings.

- Delivery and inspection of electrical panels and HVAC units at the fabrication yard.

- Completion of 70% of underground utility ducts and manholes.

- Mobilization of additional manpower for MEP rough-in to accelerate field progress.

Planned Activities for Next Month

- Completion of MEP installations for Blocks A–D.

- Arrival and installation of HVAC systems.

- Commencement of plastering, tiling, and internal finishing works.

- Preparation for façade panel installation and external works.

Charts and Visuals

Insert the following visuals for management review:

- Overall project progress curve (planned vs. actual)

- Phase-wise progress bar chart (Engineering / Procurement / Construction)

- Cumulative S-curve showing progress trend over time

# 4. Cost & Schedule Performance

The project remains on budget but is slightly behind schedule relative to the approved baseline. Continuous monitoring of the Earned Value Management (EVM) indicators — specifically, the Cost Performance Index (CPI) and Schedule Performance Index (SPI) — provides early warning signals for potential variances, enabling timely corrective actions.

As at the end of October 2025, the project’s key performance indices are summarized below:

| Indicator | Formula | Current Value | Interpretation |
| --- | --- | --- | --- |
| CPI | EV / AC | 1.02 | The project is currently on budget, with actual costs slightly lower than earned value, indicating effective cost control and resource utilization. |
| SPI | EV / PV | 0.94 | The project is slightly behind schedule, mainly due to delayed façade panel fabrication and extended rainfall periods affecting field productivity. |

The CPI value of 1.02 signifies that for every ₦1.00 spent, the project has earned ₦1.02 in value — reflecting a positive cost variance. Conversely, the SPI value of 0.94 implies that the project has achieved 94% of the planned work for this reporting period, suggesting a manageable schedule variance that requires attention.

To recover lost time, the project team has implemented several schedule optimization measures, including:

- Increasing manpower for key activities such as MEP installations and finishing works.

- Re-sequencing non-dependent work fronts to maximize parallel execution.

- Enhancing material logistics and site coordination to minimize idle time.

- Extending work hours during favorable weather conditions.

Financially, the project continues to operate within the approved Baseline Budget (BAC) of ₦2.4 billion, with commitments and expenditures well-aligned to the financial forecast. No cost overruns are anticipated at this stage, and contingency provisions remain adequate.

Charts and Visuals

(To be inserted as visuals in the report document)

- Figure 1: Cumulative Cost vs. Time (S-Curve) — Planned Value (PV), Earned Value (EV), and Actual Cost (AC).

- Figure 2: CPI and SPI trend chart showing performance stability over recent months.

- Figure 3: Monthly expenditure histogram (optional, if financial tracking is detailed).

# 5. Quality, Health, Safety & Environment (QHSE)

The project continues to maintain strong performance in Quality, Health, Safety, and Environmental (QHSE) management, in alignment with Shark Inc. and WorkFlowKits EPC Ltd. corporate standards. The reporting month of October 2025 recorded zero Lost Time Incidents (LTI), maintaining the project’s exemplary safety record since commencement. A total of five (5) minor first-aid cases were reported, all of which were promptly treated and closed with no escalation or reoccurrence.

Health and Safety Performance

The cumulative man-hours worked on the project as at the end of October 2025 stands at approximately 285,000 man-hours with zero LTI. This achievement underscores the project team’s proactive commitment to a “Goal Zero” culture — preventing harm to people, environment, and assets.

Key safety initiatives implemented during the period include:

- Daily toolbox talks emphasizing hazard awareness, proper use of PPE, and task-specific risk mitigation.

- Weekly safety leadership walks by the Project and HSE Management teams.

- Monthly joint safety meetings with subcontractors to review incident trends and lessons learned.

- Implementation of a Permit-to-Work (PTW) audit program, ensuring compliance with safe work procedures.

Quality Performance

Quality control and assurance processes continue to yield positive results. Inspections across civil, structural, and MEP disciplines indicate an average 98% compliance rate with project specifications and quality standards.
Key highlights include:

- Successful completion of material verification for structural steel and reinforcement bars.

- Approval of key inspection and test plans (ITPs) and quality dossiers.

- Closure of 95% of non-conformance reports (NCRs) raised in previous months.

- Enhanced coordination between QA/QC and Construction teams to ensure early detection and correction of potential quality deviations.

Environmental Management

Environmental stewardship remains an integral part of project execution. Regular monitoring of waste segregation, spill prevention, and noise/dust control measures have ensured compliance with local environmental regulations.
Additional initiatives include:

- Controlled waste disposal through certified contractors.

- Routine site environmental audits and awareness campaigns.

- Reuse of excavated material where feasible to minimize waste footprint.

Summary of QHSE Performance Indicators

| Indicator | This Month | Cumulative | Remarks |
| --- | --- | --- | --- |
| Lost Time Incidents (LTI) | 0 | 0 | No LTI since project start |
| First Aid Cases | 5 | 17 | All treated and closed |
| Near Misses Reported | 3 | 11 | Corrective actions implemented |
| Quality Compliance | 98% | 97% | Within target range |
| Environmental Non-Conformances | 0 | 0 | Fully compliant |

Charts and Visuals

(To be inserted in the Word document)

- Figure 1: Monthly Safety Performance Trend (Total Recordable Incidents, LTI Frequency Rate).

- Figure 2: Quality Inspection Compliance Trend.

- Figure 3: Environmental Performance Chart (Waste Segregation, Water & Energy Use).

# 6. Risk Management

Risk management remains a critical component of project control and performance assurance. The project team continues to proactively identify, assess, and mitigate potential risks that could impact scope, schedule, cost, quality, or safety objectives. Risk reviews are held bi-weekly, involving key stakeholders from engineering, procurement, construction, and HSE disciplines to ensure timely updates and mitigation planning.

As at the end of October 2025, the following represent the Top Five (5) active project risks and their corresponding mitigation measures:

| Risk ID | Risk Description | Impact | Probability | Mitigation / Current Action |
| --- | --- | --- | --- | --- |
| R.3 | 1. Delay in façade panel supply | High | Medium | Vendor engagement intensified; alternate supplier identified; logistics expediting initiated to recover delay. |
| R.9 | 2. Weather disruption (prolonged rainfall) | Medium | High | Work schedule re-sequenced to prioritize indoor and non-weather-dependent activities; use of weather monitoring tools for work planning. |
| R.14 | 3. Labour shortage for specialized trades | Medium | Medium | Recruitment drive and subcontractor mobilization plan implemented to reinforce workforce in critical areas (MEP and finishing). |
| R.16 | 4. Material price fluctuation (steel and finishing items) | High | Low | Advance bulk procurement and price locking in framework agreements to minimize exposure. |
| R.20 | 5. Equipment breakdown (cranes, mixers, lifts) | Low | Low | Preventive maintenance program reinforced; standby equipment and spares allocated to reduce downtime risk. |

Key Risk Trends and Insights

- The façade panel supply delay remains the most significant schedule risk but is being closely managed through vendor follow-up and logistics monitoring.

- Weather-related delays have moderated with improved work sequencing and early morning/extended-hour shifts during dry windows.

- No new critical risks have emerged during this reporting period; however, labour availability and vendor performance continue to require close supervision.

- The overall project risk exposure remains within acceptable tolerance levels, with mitigation actions effectively controlling potential cost and time impacts.

Ongoing Risk Management Initiatives

- Weekly cross-functional risk review meetings with visual tracking dashboards.

- Continuous update of the project risk register with probability–impact scoring.

- Monthly escalation of high and critical risks to the Project Steering Committee.

- Integration of lessons learned into ongoing execution planning.

Charts and Visuals

(To be inserted in the Word document)

- Figure 1: Project Risk Heat Map showing relative positioning of active risks by probability and impact.

- Figure 2: Risk Exposure Trend (Cumulative High/Medium/Low risks).

- Figure 3: Risk Closure Progress Chart.

# 7. Key Issues and Concerns

The project team continues to monitor and manage several operational and coordination challenges that have affected progress during the reporting period. While none of the issues pose critical threats to overall project completion, timely intervention is necessary to prevent escalation and safeguard schedule integrity.

| Issue Description | Impact / Consequence | Current Status | Mitigation / Next Steps |
| --- | --- | --- | --- |
| 1. Delayed façade panel delivery impacting Block B progress | Delay in external cladding and finishing activities; potential slippage of Block B handover by 2–3 weeks. | Vendor production backlog identified; delivery rescheduled for mid-November 2025. | Continuous vendor follow-up; alternate fabrication vendor shortlisted; installation sequencing revised to prioritize Blocks A and C. |
| 2. Heavy rains causing reduced site productivity | Civil and external works slowed; limited working hours during downpours. | Weather disruption reduced effective workdays by ~15% during October. | Implementing extended shifts on dry days; introducing covered work zones for finishing and indoor works; re-sequencing outdoor scopes. |
| 3. Limited manpower availability for electrical works | Slow progress on MEP rough-in activities; risk of delaying subsequent finishing. | Subcontractor manpower reduced due to parallel project commitments. | Approved manpower reinforcement plan; onboarding additional electricians and helpers; weekly progress tracking introduced. |
| 4. Need for expedited approvals on design change requests | Potential delay in procurement and construction execution; affects schedule alignment between design and site. | Pending approval for minor design modifications on façade and drainage layouts. | Coordination meeting held with client representatives; commitment received for fast-track review and response cycle. |

Summary and Outlook

Most of the above issues are being actively addressed through collaborative planning between Shark Inc., WorkFlowKits EPC Ltd., and the subcontractor teams.
The key focus for the next period will be to ensure on-time façade panel delivery, recover lost productivity from weather downtime, and sustain manpower levels for critical path works.
With continued emphasis on coordination and early decision-making, the project is expected to realign with the baseline schedule in the upcoming months.

# 8. Upcoming Milestones / Next Period Plan

The project remains on course toward achieving key deliverables for the next reporting period. The upcoming month will focus on advancing construction works across all active fronts, completing major MEP installations, and preparing for the transition into finishing and external development activities.

Planned Milestones for Next Period

| Milestone / Activity | Target Completion Date | Remarks / Expected Outcome |
| --- | --- | --- |
| Completion of electrical rough-ins for Blocks A–D | November 2025 (Week 2) | Critical to enable wall closure and subsequent finishing works; manpower reinforcement ongoing to ensure timely completion. |
| Arrival and installation of final HVAC equipment | November 2025 (Week 3) | All major HVAC components cleared at the port; site installation to commence immediately upon delivery. |
| Mobilization of finishing contractor | November 2025 (Week 3) | Contractor mobilization and induction planned; priority on Blocks A and B to achieve early handover readiness. |
| Kick-off for landscaping and external works | November 2025 (Week 4) | Scope includes drainage connections, road paving, and external lighting; to commence in parallel with building finishes. |
| Initiation of façade installation works | Early December 2025 | Dependent on façade panel delivery; revised schedule issued to align with material readiness. |

Focus Areas for Next Month

- Sustain construction momentum across multiple blocks by maintaining adequate manpower and equipment resources.

- Achieve mechanical completion of electrical and plumbing installations for the first set of blocks.

- Commence finishing activities, starting with tiling, ceiling, and internal painting works.

- Maintain safety performance with targeted behavioral safety campaigns during the high-activity phase.

- Update procurement close-out plan and confirm readiness of all balance materials for site use.

Forward Outlook

The next reporting period is expected to mark a transition from structural works to finishing and completion activities. The focus will be on achieving visible progress on interiors and façade installations, maintaining schedule discipline, and ensuring zero rework through enhanced quality checks. With timely delivery of pending materials and consistent field productivity, the project remains on track to achieve substantial completion within Q2 2026.

# 9. Appendices

Appendix A: Progress Photos (Insert placeholders).

Appendix B: Updated Schedule Snapshot (Insert Gantt Chart).

Appendix C: Key Correspondences (if required).