## Home
#VALUE! | PROJECT RISK REGISTER
Project Information & Quick Guide
Project Information |  | #VALUE!
Project Title: | Amaken 65km Trunkline Pipeline Project
Project Code: | PRD24/0234
Project Manager: | John Cole
Date Created: | 2025-10-23
Version: | R01
Prepared By:
Reviewed By:
Approved By:
Quick Guide — How to Use This Tool |  |  | Quick Navigation
1) Use the Register sheet to log and update risks. |  |  | → Go to Register
2) Use dropdowns for Category, Status, and Review Frequency.
3) Enter Probability & Impact (1–5) — scores and RAG auto-calc. |  |  | → Go to Dashboard
4) Maintain Target Date, Last Review Date, and Review Freq for governance.
5) Matrix shows the heat-map; Report shows KPIs and creates a printable summary. |  |  | → Go to Matrix
6) Edit lists in Lookup (Categories, Statuses, Scales).
7) Avoid deleting formula columns; extend rows if needed. |  |  | → Go to Report
8) Save versioned copies (Risk_Register_v1.0.xlsx, v1.1, etc.).

## Lookup (hidden)
Probability_Scale | Impact_Scale | Status_List | Category_List | Review_Frequency_Days | Detectability
1 - Rare | 1 - Insignificant | Open | Technical | 7 | 1 – Very Easy to Detect
2 - Unlikely | 2 - Minor | In Progress | Economical | 14 | 2 – Easy to Detect
3 - Possible | 3 - Moderate | Mitigating | Commercial | 30 | 3 – Moderate Detectability
4 - Likely | 4 - Major | Accepted | Organizational | 60 | 4 – Hard to Detect
5 - Almost Certain | 5 - Severe | Transferred | Political | 90 | 5 – Very Hard to Detect
Closed

## Register
Risk ID | Risk Title | Risk Description | Risk Owner | Category | Identified Date | Status | Probability (1-5) | Impact (1-5) | Detectability (1-5) | Inherent Score | Residual Probability | Residual Impact | Residual Score | Risk Priority Number (RPN) | Target Date | Days Open | Days to Due | Residual RAG | Mitigation Plan | Contingency Plan | Triggers | Cost Impact (₦) | Schedule Impact (days) | Last Review Date | Review Freq (days) | Next Review Due
R-0001 | Delay in Material Delivery | Key equipment and piping materials sourced from overseas may experience shipping delays due to customs clearance issues or vendor backlog, leading to schedule slippage on site. | John C. | Technical | 2025-10-23 | In Progress | 4 - Likely | 4 - Major | 4 – Hard to Detect | 16 | 4 - Likely | 2 - Minor | 8 | 64 | 2028-12-06 | 13 | 1127 | Amber | 1. Engage logistics team early to monitor shipment tracking and customs processes. 2. Maintain a 10% schedule float for critical materials. 3. Identify local backup suppliers for fast-moving items. |  |  |  |  | 2025-10-15 | 14 | 2025-11-06
R-0002 | Interface Misalignment Between EPC Contractors | Mechanical tie-in points between EPC Package A and Package B may not align as per design coordinates, causing rework and schedule delays. | Emeka I. | Technical | 2025-10-23 | Open | 3 - Possible | 4 - Major | 5 – Very Hard to Detect | 12 | 2 - Unlikely | 2 - Minor | 4 | 60 | 2028-10-10 | 13 | 1070 | Green | 1. Conduct joint interface verification and 3D model reviews before fabrication. 2. Assign a dedicated interface coordinator. 3. Approve tie-in coordinates through an integrated review session. |  |  |  |  | 2025-10-16 | 30 | 2025-11-22
R-0003 | Delay in Material Delivery | Key equipment and piping materials sourced from overseas may experience shipping delays due to customs clearance issues or vendor backlog, leading to schedule slippage on site. | John C. | Commercial | 2025-10-24 | Open | 5 - Almost Certain | 4 - Major | 4 – Hard to Detect | 20 | 3 - Possible | 4 - Major | 12 | 80 | 2028-10-11 | 12 | 1071 | Amber | 1. Engage logistics team early to monitor shipment tracking and customs processes. 2. Maintain a 10% schedule float for critical materials. 3. Identify local backup suppliers for fast-moving items. |  |  |  |  | 2025-10-10 | 14 | 2025-11-07
R-0004 | Interface Misalignment Between EPC Contractors | Mechanical tie-in points between EPC Package A and Package B may not align as per design coordinates, causing rework and schedule delays. | Emeka I. | Technical | 2025-10-23 | Open | 4 - Likely | 4 - Major | 4 – Hard to Detect | 16 | 2 - Unlikely | 3 - Moderate | 6 | 64 | 2028-10-10 | 13 | 1070 | Green | 1. Conduct joint interface verification and 3D model reviews before fabrication. 2. Assign a dedicated interface coordinator. 3. Approve tie-in coordinates through an integrated review session. |  |  |  |  | 2025-10-16 | 30 | 2025-11-22
R-0005 | Inaccurate Tie-In Coordinates | The actual field coordinates and elevations of the tie-in points differ from design drawings, leading to potential clash, rework, and schedule delay during installation. | Emma G. | Technical | 2025-10-23 | Open | 2 - Unlikely | 3 - Moderate | 3 – Moderate Detectability | 6 | 2 - Unlikely | 3 - Moderate | 6 | 18 | 2028-10-10 | 13 | 1070 | Green | 1. Conduct joint site verification with contractor before fabrication. 2. Update isometric drawings to reflect as-built conditions. 3. Include survey verification as part of pre-construction checklist. |  |  |  |  | 2025-11-05 | 60 | 2026-01-04
R-0006 | Delay in Material Delivery | Late delivery of critical materials such as valves and fittings from the supplier may stall construction progress and impact project completion. | Jude O. | Technical | 2025-11-02 | In Progress | 2 - Unlikely | 4 - Major | 4 – Hard to Detect | 8 | 3 - Possible | 3 - Moderate | 9 | 32 | 2028-10-10 | 3 | 1070 | Amber | 1. Engage procurement early and track long-lead items weekly. 2. Maintain buffer stock for critical materials. 3. Include penalty clauses for supplier delays. |  |  |  |  | 2025-11-05 | 60 | 2026-01-04
R-0007 | Equipment Failure During Commissioning | New electrical switchgear or control panels may fail functional tests due to manufacturing defects or improper FAT testing, leading to rework and project delays. | Emeka I. | Technical | 2025-11-02 | Open | 2 - Unlikely | 2 - Minor | 4 – Hard to Detect | 4 | 2 - Unlikely | 3 - Moderate | 6 | 16 | 2028-10-10 | 3 | 1070 | Green | 1. Ensure OEM presence during FAT and SAT. 2. Conduct pre-commissioning functional checks with OEM representatives. 3. Keep critical spare parts available on site. |  |  |  |  | 2025-11-05 | 60 | 2026-01-04
R-0008 | Concurrent Operations Delay (SIMOPS) | Overlapping activities between Operations and Project teams at live plant areas may restrict work windows and affect project progress. | Mary J. | Technical | 2025-11-04 | Open | 5 - Almost Certain | 4 - Major | 4 – Hard to Detect | 20 | 3 - Possible | 3 - Moderate | 9 | 80 | 2028-10-10 | 1 | 1070 | Amber | 1. Develop a detailed SIMOPS plan jointly with Operations. 2. Sequence critical tie-ins during planned maintenance windows. 3. Obtain daily work permits with clear isolation boundaries. |  |  |  |  | 2025-11-05 | 30 | 2025-12-05
R-0009 | Equipment Failure During Commissioning | New electrical switchgear or control panels may fail functional tests due to manufacturing defects or improper FAT testing, leading to rework and project delays. | Emeka I. | Technical | 2025-11-02 | Open | 3 - Possible | 4 - Major | 4 – Hard to Detect | 12 | 2 - Unlikely | 3 - Moderate | 6 | 48 | 2028-10-10 | 3 | 1070 | Green | 1. Ensure OEM presence during FAT and SAT. 2. Conduct pre-commissioning functional checks with OEM representatives. 3. Keep critical spare parts available on site. |  |  |  |  | 2025-11-05 | 60 | 2026-01-04
Formulas:
Days Open = LET(_xlpm.last, AGGREGATE(14,6,ROW([Risk Title]:B1048576)/([Risk Title]:B1048576<>""),1), _xlpm.f, [Identified Date]:INDEX(F:F,_xlpm.last), _xlpm.g, [Status]:INDEX(G:G,_xlpm.last), IF((_xlpm.g="Closed")+(_xlpm.f=""),"",TODAY()-_xlpm.f))
Days to Due = LET(_xlpm.last, AGGREGATE(14,6,ROW([Risk Title]:B1048576)/([Risk Title]:B1048576<>""),1), _xlpm.g, [Status]:INDEX(G:G,_xlpm.last), _xlpm.p, [Target Date]:INDEX(P:P,_xlpm.last),IF((_xlpm.g="Closed")+(_xlpm.p=""),"", _xlpm.p - TODAY()))

## Matrix
RISK HEATMAP
Risk Matrix (Open risks only) |  | IMPACT (Consequence/Severity)
|  | 1 | 2 | 3 | 4 | 5
PROBABILITY (Likelihood) | 1 | 0 | 0 | 0 | 0 | 0
| 2 | 0 | 1 | 1 | 1 | 0
| 3 | 0 | 0 | 0 | 2 | 0
| 4 | 0 | 0 | 0 | 2 | 0
| 5 | 0 | 0 | 0 | 2 | 0
4x4, 4x5,5x4 and 5x5 will be Dark Red

## Report
Risk Report Summary
Project: | Amaken 65km Trunkline Pipeline Project
Project Code: | PRD24/0234
Project Manager: | John Cole
Report Date: | 2025-11-05
Key Metrics
Total Risks (all): 9 | Red (Residual ≥15): 0 |  | Number of Red RPN | 4 |  | Technical | 8
[6 empty] | Economical | 0
Open (not Closed): 9 | Amber (Residual 8–14): 4 |  | Number of Red Residual RAG | 0 |  | Commercial | 1
[6 empty] | Organizational | 0
Closed: 0 | Green (Residual ≤7): 5 |  | Overdue (Days to Due < 0) | 0 |  | Political | 0
|  |  | Due in 0–7 days | 2
Top Red Risks (Open & RPN ≥ 64)
Risk ID | Title | Owner | Category | RPN | Days to Due | Status | Target Date
R-0001 | Delay in Material Delivery | John C. | Technical | 64 | 1127 | In Progress | 47093
R-0003 | Delay in Material Delivery | John C. | Commercial | 80 | 1071 | Open | 47037
R-0004 | Interface Misalignment Between EPC Contractors | Emeka I. | Technical | 64 | 1070 | Open | 47036
R-0008 | Concurrent Operations Delay (SIMOPS) | Mary J. | Technical | 80 | 1070 | Open | 47036
Upcoming Reviews (Due in 0–7 days)
Risk ID | Title | Owner | Category | RPN | Days to Due | Status | Target Date
R-0001 | Delay in Material Delivery | John C. | Technical | 64 | 1 | In Progress | 47093
R-0003 | Delay in Material Delivery | John C. | Commercial | 80 | 2 | Open | 47037

## Data (hidden)
Owner | High | Medium | Low
Emeka I. | 1 | 2 | 1
Emma G. | 0 | 0 | 1
John C. | 2 | 0 | 0
Jude O. | 0 | 1 | 0
Mary J. | 1 | 0 | 0

## Guide
Guide
DETECTABILITY |  |  | PASSWORD TO UNLOCK SHEET
Score | Description | Meaning / Example | 12345
1 – Very Easy to Detect | Issue almost always detected immediately through alarms, routine checks, or automation. | e.g., continuous monitoring or built-in safety trip.
2 – Easy to Detect | High chance of early detection before consequence; simple inspection or control likely to catch it. | e.g., visible leak, clear parameter deviation, operator checklists.
3 – Moderate Detectability | Possible to detect before impact, but depends on experience, timing, or detailed inspection. | e.g., condition monitoring or periodic inspection needed.
4 – Hard to Detect | Low chance of detection until after problem starts; requires specialized tools or infrequent checks. | e.g., hidden corrosion, complex subsystem faults.
5 – Very Hard to Detect | Practically undetectable before failure; no monitoring or warning indicators exist. | e.g., latent defect, buried/encapsulated component failure.