# PROJECT EXECUTION PLAN (PEP)

EPCC for the 70 km Amaken Gas Trunkline Project

Revision: A01

Date: May 2025

Table of Contents

1.0	Introduction	6

1.1 Purpose	6

1.2 Objectives	6

1.3 Audience and Applicability	6

1.4 PEP Structure	6

1.5 Reference Documents	6

1.6 Document Control & Revision History	7

2.0	Project Overview	7

2.1 Background	7

2.2 Project Description	7

2.3 Key Project Data	8

2.4 Strategic Alignment	8

3.0	Opportunity Statement & Value Drivers	8

3.2 Value Drivers	8

3.3 Sustainability & ESG	9

4.0	Project Scope	9

4.1 Scope by Discipline	9

4.2 Out-of-Scope	9

4.3 Battery Limits & Interfaces	9

5.0	Execution Philosophy	10

5.1 Overall Approach	10

5.2 Execution Stages	10

5.3 Execution Principles	10

5.4 Key Assumptions & Constraints	10

6.0	Project Objectives & KPIs	11

6.1 Objectives	11

6.2 KPIs & Measurement	11

7.0	Engineering Management Plan (Expanded)	11

7.1 Purpose	11

7.2 Execution Philosophy	12

7.3 Design Basis & Standards	12

7.4 Design Verification & Validation	12

7.5 Inter-Discipline Checks & Reviews	12

7.6 Software & Tools	12

7.7 Deliverables & Review Cycles	12

7.8 Progress Measurement	12

7.9 Design Change Management	13

7.10 Document Control in Engineering	13

7.11 Engineering Interfaces	13

7.12 Records & Archival	13

8.0	Procurement Management Plan	13

8.1 Objective & Philosophy	13

8.2 Process Flow	13

8.3 Vendor Qualification	13

8.4 Inspection/Expediting & FAT	13

8.5 Logistics & Material Control	13

9.0	Construction Management Plan	14

9.1 Construction Strategy	14

9.2 WBS (Excerpt)	16

9.3 Equipment & Resources (Excerpt)	16

9.4 HSSE Sub-Plan (Construction)	16

9.5 Quality Sub-Plan (Construction)	16

9.6 Logistics & Resource Plan	17

10.0	Commissioning & Start-Up Plan	17

10.1 Pre-Commissioning	17

10.2 Commissioning	17

10.3 Handover & Acceptance	17

11.0	Interface Management Plan	17

11.1 Objectives	17

11.2 Interface Types	17

12.0	Organization & Responsibilities	19

12.1 Governance	19

12.2 Roles & Responsibilities (Excerpt)	19

12.3 Authority Matrix (Excerpt)	21

13.0	Project Controls & Schedule Management Plan	22

13.1 Planning Philosophy	22

13.2 Baseline & Milestones (Illustrative)	22

13.3 Progress & EVM	22

13.4 Reporting	22

14.0	Contracting & Procurement Strategy	22

14.1 Contracting Philosophy	22

14.2 Tendering & Award	22

14.3 Key Contract Provisions (Illustrative)	22

14.4 Strategy Table	23

15.0	Risk Management Plan	23

15.1 Methodology	23

15.2 Sample Risk Register (Excerpt)	23

15.3 Opportunity Management	24

16.0	Change Management Plan	24

16.1 Process	24

16.2 Approvals (Illustrative)	24

17.0	Document Control Plan	24

17.1 System & Numbering	24

17.2 Transmittals & Distribution	24

17.3 Retention & Archival	24

18.0	Local Content & Community Relations Plan	25

18.1 LC Targets	25

18.2 Community Engagement	25

19.0	Environmental & Sustainability Plan	25

19.1 Objectives	25

19.2 Controls	25

20.0	Project Deliverables & Close-Out	25

20.1 Deliverables Matrix (Excerpt)	25

20.2 Lessons Learned	26

20.3 Final Handover	26

21.0	Appendices	26

PART 1: (Introduction → Project Overview → Opportunity & Value → Scope → Execution Philosophy)

# Introduction

## 1.1 Purpose

This Project Execution Plan (PEP) defines the strategy, organization, and control framework to safely, predictably, and cost-effectively deliver the EPCC for the 70 km Amaken Gas Trunkline Project. It specifies how the project will be governed and executed from contract award through engineering, procurement, construction, pre-commissioning, commissioning, and handover to Operations. This PEP is a live, controlled document; revisions will be issued when material changes occur (scope, strategy, schedule, or policy).

## 1.2 Objectives

- Safety: Achieve zero harm to people and environment by embedding HSSE risk management into planning and field execution.

- Quality: Deliver assets that conform to specifications, codes, and statutory requirements, first time.

- Schedule & Cost: Meet approved milestones and budget via robust planning, progress measurement, and change control.

- Stakeholder Confidence: Provide transparent reporting and effective interface management with authorities, communities, and partners.

- Value: Maximize local content, reduce lifecycle costs, and capture lessons learned.

## 1.3 Audience and Applicability

This PEP applies to Shark Inc.’s Project Steering Committee (PSC), Project Management Team (PMT), the EPCC Contractor (once awarded), subcontractors, vendors, and third-party assurance bodies. It governs all project phases and supersedes lower-tier procedures in case of conflict (unless statutory constraints apply).

## 1.4 PEP Structure

The PEP consolidates all subordinate management plans—Engineering, Procurement, Construction (with HSSE and Quality sub-plans), Commissioning & Start-up, Interface, Project Controls, Contracting & Procurement Strategy, Risk, Change, Document Control, Local Content & Community Relations, Environmental & Sustainability, and Deliverables/Handover. Cross-references are provided where processes intersect.

## 1.5 Reference Documents

- FEED Report – Amaken Gas Trunkline

- Shark Inc. Project Management System (PMS) Manual

- Codes & Standards: ASME B31.8 (Gas Transmission), API 5L (Line Pipe), ASME IX (Welding), ISO 9001 (Quality), ISO 14001 (Environment), ISO 45001 (OH&S), ISO 3183 (Pipeline Transportation Systems)

- National regulations and permits (environmental, right-of-way, utilities, transport)

- IFC Performance Standards (for ESIA alignment)

## 1.6 Document Control & Revision History

The Document Controller maintains the master in the EDMS with unique numbering and revision status. Revisions are reviewed/approved by the PM and PSC as applicable. Distribution is controlled via transmittals.

Table 1 – Document Revision History (Template)
| Rev | Date | Description of Change | Prepared by | Reviewed by | Approved by |
|---|---|---|---|---|---|
| 0 | [Insert] | Initial Issue – Draft for Review | PPM | PSC | Client Director |

# Project Overview

## 2.1 Background

The Amaken region hosts significant gas resources with limited evacuation infrastructure. The trunkline project addresses this constraint by providing a strategic transmission corridor that ties the Amaken Gas Gathering Station (AGGS) to the Kolu Metering Station (KMS) and the national grid, enabling monetization of gas, supporting industrialization, and reducing flaring.

## 2.2 Project Description

The project consists of a 24-inch, ~70 km high-pressure gas trunkline traversing farmland, light forest, and transitional swamp, including road/watercourse crossings to be executed per approved methods. Major facilities include:

- Mainline Block Valve Stations (approx. every 15 km) with fencing, earthing, and drainage.

- Pig Launcher/Receiver Stations at AGGS/KMS.

- Cathodic Protection (CP) System with transformer-rectifiers and test posts.

- Telemetry/SCADA for supervisory monitoring and control.

- Tie-ins to existing infrastructure at AGGS and KMS battery limits.

Figure 1 – Indicative Route Map of Amaken Gas Trunkline (Placeholder)

## 2.3 Key Project Data

| Parameter | Description |
| --- | --- |
| Pipeline Length | ~70 km |
| Nominal Diameter | 24 in |
| Design Pressure | 70 barg (final per design) |
| Medium | Dry Natural Gas |
| Design Codes | ASME B31.8, API 5L, ISO 3183 |
| Contract Type | EPCC (Lump Sum Turnkey) |
| Planned Duration | ~24 months from award |
| Client | Shark Inc. |
| Contractor | To Be Determined |

Narrative: The pipeline design basis will be confirmed during detailed design. Hydraulic capacity and operating envelope will consider peak and turndown throughput, line pack, and temperature/pressure profiles to ensure operability and integrity across seasonal conditions.

## 2.4 Strategic Alignment

The project supports Shark Inc.’s strategy to expand midstream gas infrastructure, aligns with national decarbonization via gas-for-growth policies, and contributes to industrial competitiveness by improving energy availability and reliability.

# Opportunity Statement & Value Drivers

3.1 Opportunity Statement

The trunkline unlocks stranded/underutilized gas reserves, enabling sales to industrial hubs and power plants along the corridor and the national grid. It replaces intermittent trucking and localized flaring with a safe, continuous, metered transmission solution.

## 3.2 Value Drivers

- Revenue & Throughput: Designed capacity circa 250 MMSCFD, scalable with compression upgrades.

- Environmental: Significant flare reduction, translating into CO₂-equivalent avoidance and ESG improvement.

- Reliability: Telemetry, CP, and block-valve segmentation improve uptime and maintenance flexibility.

- Local Content: >45% local man-hours and substantial local procurement and fabrication.

- Community Benefits: Jobs, upskilling, and CSR programs underpin social license to operate.

## 3.3 Sustainability & ESG

The project will be developed consistent with IFC Performance Standards and national ESIA requirements. Sustainable practices include erosion/sediment control, habitat reinstatement, responsible waste management, spill prevention, and community grievance mechanisms.

# Project Scope

## 4.1 Scope by Discipline

Engineering: Route/topographical survey; geotechnical/hydrological studies; detailed design; stress/hydraulic analysis; crossings design; design safety reviews (HAZID/HAZOP); 3-D model reviews; as-built documentation.
Procurement: Line pipe, induction bends, fittings, valves, CP equipment, instrumentation, skids; vendor qualification; QA surveillance; expediting; logistics; customs clearance; storage and preservation.
Construction: ROW clearing/grading; trenching; stringing; bending; welding (auto/manual), NDT (RT/UT/PAUT); field joint coating; lowering-in; backfilling; crossings; valve stations; CP installation; hydrotesting; reinstatement.
Commissioning: Cleaning/gauging; hydrotest; dewatering/drying; nitrogen purge; leak testing; SCADA integration; gas-in; performance verification; turnover/handover.

Figure 2 – Scope Boundary Illustration (Placeholder)

## 4.2 Out-of-Scope

- Upstream processing/compression beyond AGGS.

- Downstream metering beyond KMS battery limit.

- Operations & Maintenance after handover (separate governance).

## 4.3 Battery Limits & Interfaces

Battery limits are fixed at the launcher (AGGS) and receiver (KMS) flanges. Interfaces include power supply, communications, corridor access, and existing utility crossings. The Interface Management Plan defines owners, registers, and review cadence.

# Execution Philosophy

## 5.1 Overall Approach

A single EPCC contracting model achieves end-to-end accountability, minimizes interface risks, and aligns engineering deliverables with procurement and construction realities. Shark Inc. will provide governance via the PSC and day-to-day oversight via the PMT; the EPCC Contractor delivers the full scope to IFC drawings, specifications, and codes.

## 5.2 Execution Stages

- Pre-Award: Tendering, clarifications, evaluations, award recommendation.

- Detailed Engineering: Design deliverables, reviews (30/60/90%), constructability integration, IFC issuance.

- Procurement & Fabrication: MRs, POs, surveillance, FATs, logistics, preservation.

- Construction: Site establishment; pipeline works; stations/CP; hydrotesting; reinstatement.

- Commissioning & Handover: Drying, leak/punch closure, performance tests, dossiers, as-builts.

## 5.3 Execution Principles

- Safety-by-Design & Execution: Risk identification and hierarchy of controls embedded in work planning.

- Predictable Delivery: Integrated plan (schedule, cost, risk) and clear daily/weekly control cycles.

- Quality Built-In: Prevention over detection; clear ITPs and hold points; defect-free turnover.

- Stakeholder Engagement: Proactive communications plan with communities/regulators.

- Digital Enablement: EDMS, progress dashboards, and model reviews for transparency.

Figure 3 – Typical ROW Construction Activities (Placeholder)

## 5.4 Key Assumptions & Constraints

| Item | Assumption/Constraint | Implication |
| --- | --- | --- |
| ROW Access | Client to secure ROW timely | Mobilization sequencing |
| Permits | Environmental/statutory approvals before site works | Gate to start of construction |
| Seasonal Windows | Dry season for heavy works | Plan high-productivity fronts |
| Security | Joint plan with authorities | Route patrols, escorts as needed |

5.5 Stakeholder Engagement

The CLO and Community Relations team will maintain regular dialogue, disclose schedule/impacts transparently, manage grievances within defined timelines, and coordinate CSR aligned to community priorities.

PART 2: (Objectives & KPIs → Engineering Plan → Procurement Plan → Construction Plan (HSSE & Quality sub-plans) → Commissioning → Interface → Organization)

# Project Objectives & KPIs

## 6.1 Objectives

- Deliver a compliant, operable trunkline within approved schedule and cost.

- HSSE: 0 LTI, 0 major environmental incident.

- Quality: ≤2% rework by weld count; all dossiers accepted at handover.

- Local Content: ≥45% local man-hours; maximize local procurement/fabrication.

- Handover: Clean, validated turnover packages and trained operations personnel.

## 6.2 KPIs & Measurement

| Category | Target/KPI | Measurement Basis |
| --- | --- | --- |
| HSSE | 0 LTI; TRIR ≤ 0.3 | Monthly HSSE Report |
| Schedule | Milestones met ±5 days | P6 Baseline vs. Actual |
| Cost | CPI ≥ 0.95; EAC ≤ +5% | EVM, cost ledger |
| Quality | ≤2% NCR rework | QA/QC Log |
| Local Content | ≥45% man-hours | LC Report |

Narrative: KPIs are reviewed weekly (operational) and monthly (PSC), with corrective actions documented and tracked to closure.

# Engineering Management Plan (Expanded)

## 7.1 Purpose

Define planning, execution, monitoring, and control of all engineering work such that deliverables are safe, compliant, constructible, maintainable, and economically optimized.

## 7.2 Execution Philosophy

Engineering led by EPCC Contractor under Shark Inc. technical governance. Stage-gate reviews (30/60/90%) culminate in IFC issue. Integrated Design Schedule (IDS) aligns with the Master Control Schedule (MCS).

## 7.3 Design Basis & Standards

ASME B31.8, API 5L, ASME IX, ISO 3183, and Shark Inc. standards apply. Deviations require MOC with engineering justification and client approval.

## 7.4 Design Verification & Validation

Multi-tier process: self-check → peer review → inter-discipline review → independent verification → validation. Comments tracked in a Design Review Tracker; all actions closed prior to IFC.

## 7.5 Inter-Discipline Checks & Reviews

- 30% Model Review: plot plans/clearances

- 60%: access, tie-ins, maintainability

- 90%: clash-free model; finalization

- Constructability Review: lifting, welding, access, and laydown constraints

Figure 4 – Typical 3-D Model Review Session (Placeholder)

## 7.6 Software & Tools

HYSYS/PIPESIM (hydraulics), CAESAR II (stress), STAAD (structures), SmartPlant/Plant3D (3-D), ETAP (electrical studies), CDEGS (CP). Licensed, validated versions only.

## 7.7 Deliverables & Review Cycles

| Discipline | Key Deliverables | Review Cycle |
| --- | --- | --- |
| Process | PFDs, P&IDs, line lists | 30/60/90/IFC |
| Pipeline | Alignment sheets, stress calc., crossings | 30/60/90 |
| Civil | ROW/layouts, foundations, drainage | 60/IFC |
| E&I | Hook-ups, loop diagrams, cable schedules | 60/90/IFC |
| CP | Layouts, sizing calc., test posts | 90/IFC |

## 7.8 Progress Measurement

Weighted deliverable list with S-curve tracking; discipline leads report weekly progress and forecasts.

## 7.9 Design Change Management

Design Change Notices (DCNs) link to the MOC process, containing technical/HSSE/schedule/cost impacts and approvals.

## 7.10 Document Control in Engineering

EDMS numbering: AGT-ENG-####-REV-Y. Status codes: IFR, IFC, IFU, AB. Transmittals acknowledged within 48 hours.

## 7.11 Engineering Interfaces

Engineering interfaces with Procurement (MRs/vendor data), Quality (V&V, audits), HSSE (HAZID/HAZOP), and Construction (FCRs).

## 7.12 Records & Archival

All records archived electronically with index; critical certificates stored in hard copy as required.

# Procurement Management Plan

## 8.1 Objective & Philosophy

Procure conforming materials/equipment on time, at best value, while meeting LC targets. Centralized procurement led by the Contractor, monitored by Shark Inc. Project Controls.

## 8.2 Process Flow

MR → ITT/RFQ → Tech & Commercial Evaluation → Award → Surveillance/Expediting → FAT → Logistics → Site receipt/preservation.

## 8.3 Vendor Qualification

Use Shark Inc. AVL; audits verify capacity, HSSE, and QA systems. Critical items (line pipe, valves) receive enhanced surveillance.

## 8.4 Inspection/Expediting & FAT

ITPs define witness/hold points. Third-party inspectors ensure compliance. Nonconformities trigger CAPA and re-inspection as needed.

## 8.5 Logistics & Material Control

Ports: Onne/Apapa. Transport to laydown yards; storage with preservation plans. SAP-MM (or equivalent) tracks receipts, issues, and stock.

Figure 5 – Typical Line Pipe Stacking at Laydown Yard (Placeholder)

# Construction Management Plan

## 9.1 Construction Strategy

The construction phase of the EPCC for the 70 km Amaken Gas Trunkline Project will be executed in a structured, controlled, and environmentally responsible manner to ensure safe, efficient, and quality-driven delivery of the pipeline and associated facilities. The strategy is designed to align with NLNG’s and Shark Inc.’s HSSE, quality, and local content requirements while minimizing disruption to host communities and the environment. Construction will progress in logical sequences along the Right of Way (ROW), coordinated with permitting, materials logistics, and interface management plans.

### Right-of-Way (ROW) Preparation

The approved 15-meter construction corridor will be established following environmental clearance and community engagement. Pre-construction surveys (topographical, environmental, and cultural heritage) will precede any vegetation clearing to confirm route alignment and sensitive areas.
Clearing and grading will be executed under strict environmental controls, with segregated topsoil storage for reinstatement.
Cultural and heritage protocols will be followed per national guidelines, and any discovered artifacts will trigger the Stop Work and Notify procedure.
Access roads and temporary worksites will be designed to minimize erosion and land disturbance, with stabilization applied as needed.

### Stringing and Bending

Pipeline stringing will be conducted using GPS-tracked equipment to ensure full traceability and correct pipe placement along the ROW. Pipes will be laid on padded skids to prevent coating damage and will be aligned according to the construction alignment sheets.
Field bending will be performed using qualified cold-bending procedures approved in the Construction Method Statements and verified by QA/QC.
All pipe handling will comply with manufacturer recommendations, ensuring coating integrity and pipe-end protection.

### Welding and Non-Destructive Testing (NDT)

Welding operations will adopt automatic or semi-automatic welding systems where feasible, to ensure productivity and weld quality consistency. Welding procedures will conform to project-specific Welding Procedure Specifications (WPS) approved by Shark Inc. and verified during pre-qualification testing.
All welders will be certified per ASME Section IX or equivalent standard, and weld data will be logged digitally for traceability.
Non-destructive testing (NDT) will follow the approved Inspection and Test Plan (ITP), requiring 100% radiographic, ultrasonic (UT), or phased-array ultrasonic (PAUT) examination of all girth welds.
NDT personnel will be certified to ISO 9712 Level II or higher, and results will be reviewed and accepted by the QA/QC Lead prior to coating.

### Coating and Lowering-In

Field joint coating will be executed per the project coating specification using compatible materials and verified surface preparation standards (e.g., SA 2½).
Each coated joint will be subject to holiday testing before acceptance.
Lowering-in will be carried out using synchronized side-booms or pipelayers equipped with load monitors and certified slings to avoid overstressing the pipe or damaging the coating.
Pipe placement within the trench will follow the approved lowering procedure, ensuring uniform bedding and spacing to prevent mechanical damage.

### Backfill and Reinstatement

After pipeline lowering, backfilling will be performed using clean, verified material free of rocks or sharp objects that could compromise coating integrity.
Compaction levels will be verified as per the project specification to maintain trench stability.
Erosion and sediment control structures (e.g., berms, silt fences, straw bales) will be installed where necessary, especially near water crossings or slopes.
Reinstatement activities will include replacement of topsoil, restoration of drainage patterns, and progressive revegetation with native species.
Post-construction environmental inspections will confirm successful rehabilitation before demobilization.

### Stations and Cathodic Protection (CP) Facilities

Construction of block valve stations, scraper traps, and cathodic protection (CP) systems will run concurrently with pipeline installation.
Works will include civil foundations, equipment supports, fencing, and drainage systems designed to control runoff and ensure site stability.
Earthing and lightning protection systems will be installed per design drawings and verified by electrical QA/QC.
Cathodic protection systems will comprise transformer/rectifier (T/R) units, test posts, and anode beds installed to design depth and spacing to achieve target protection potentials.
Final testing will include CP commissioning and baseline potential surveys prior to pipeline energization.

### Construction Management and Control

All construction activities will be governed by approved Construction Method Statements, ITPs, and Job Safety Analyses (JSAs). Daily toolbox meetings will precede all field works, emphasizing HSSE, quality, and permit-to-work requirements.
A multi-disciplinary field supervision team (Construction, HSSE, QA/QC, Engineering, and Project Controls) will monitor progress, productivity, and compliance.
Interface meetings will be held weekly between Shark Inc. and the EPCC Contractor to coordinate schedule, access, and quality objectives.
Digital reporting systems will capture daily progress, welding statistics, NDT results, and environmental records to ensure transparency and traceability.

### Key Deliverables from Construction Phase

- Approved Construction Method Statements and ITPs

- Daily Construction and HSSE Reports

- Welding/NDT Logs and QA Records

- As-built Drawings and Field Redlines

- Environmental Monitoring Reports

- Reinstatement and CP Commissioning Certificates

Figure 6 – Pipeline Lowering-In Operation (Placeholder)

## 9.2 WBS (Excerpt)

| L1 | L2 | Description |
| --- | --- | --- |
| 1.0 | 1.1 | Engineering – design deliverables |
| 2.0 | 2.1 | Procurement – line pipe/valves |
| 3.0 | 3.1 | Construction – ROW/trenching |
| 3.0 | 3.2 | Construction – welding/NDT |
| 3.0 | 3.3 | Construction – testing/reinstatement |

## 9.3 Equipment & Resources (Excerpt)

| Category | Qty | Notes |
| --- | --- | --- |
| Side-booms | 12 | 24-inch pipe handling |
| Welders | 40 | Auto/manual mix |
| Excavators/Dozers | 15 | ROW & trenching |
| Trailers/Trucks | 25 | Pipe/material moves |
| Hydro Pumps | 4 | Pressure tests |

## 9.4 HSSE Sub-Plan (Construction)

Objective: Zero harm. Programs: JHA/PTW/SIMOPS; ERP with drills; journey management; dust/noise control; spill prevention; waste segregation; biodiversity protection. Roles: PM (accountable), HSE Manager (implementation), Supervisors (toolbox talks & PTW), Workforce (SWA).

Figure 7 – Site Safety Briefing / Toolbox Talk (Placeholder)

## 9.5 Quality Sub-Plan (Construction)

ISO 9001 QMS; ITPs with hold points; 100% weld RT acceptance per ASME IX; coating holidays testing; hydrotest at 1.25 × DP; NCR/CAPA and lessons learned; quality dossiers per subsystem.

Figure 8 – Field Welding Inspection (Placeholder)

## 9.6 Logistics & Resource Plan

Access roads, transport scheduling, laydown layout, manpower curves by craft, and camp/clinic arrangements included in the Construction Logistics Plan.

# Commissioning & Start-Up Plan

## 10.1 Pre-Commissioning

Cleaning/gauging pigs; hydrotest at 1.25 × DP; dewatering and drying to dew point ≤ −20 °C; nitrogen purging.

## 10.2 Commissioning

Pressurization and leak tests; valve/actuator checks; SCADA telemetry verification; readiness review and punch-list closure.

## 10.3 Handover & Acceptance

Subsystem Mechanical Completion (MC) certificates; Turnover Packages (TOPs) with as-builts, ITRs, and calibration/pressure test records; final walkdowns and acceptance.

Figure 9 – Pipeline Hydrotest Activity (Placeholder)

# Interface Management Plan

## 11.1 Objectives

Ensure timely identification, ownership, and closure of all internal/external interface points to prevent schedule or quality risks.

## 11.2 Interface Types

| Category | Examples |
| --- | --- |
| Internal | Eng ↔ Proc ↔ Constr; HSSE ↔ Ops |
| External | Regulators, utilities, communities |
| Contractual | Subcontractors, inspectors |
| Operational | Existing assets at KMS |

Interface Control Matrix (ICM) assigns an owner and due date; monthly interface meetings resolve open items.

Figure 10 – Interface Workflow Diagram (Placeholder)

# Organization & Responsibilities

## 12.1 Governance

PSC provides strategic oversight; PMT manages delivery. The EPCC Contractor provides a single point of accountability for scope, cost, schedule, quality, and HSSE performance.

Figure 11 – Project Organization Chart (Placeholder)

## 12.2 Roles & Responsibilities (Excerpt)

| Role / Position | Primary Responsibilities | Key Interfaces |
| --- | --- | --- |
| Project Steering Committee (PSC) | Provides strategic direction and governance; approves major project decisions, budgets, and changes; ensures alignment with corporate strategy. | Project Director, Business Opportunity Manager (BOM), Senior Management |
| Project Director | Overall accountability for project execution and delivery; ensures compliance with project objectives, safety, schedule, and cost; chairs project reviews. | PSC, BOM, Project Manager, EPC Contractor PM |
| Business Opportunity Manager (BOM) | Owns the business case; ensures project alignment with economic drivers and long-term value; provides strategic oversight on funding, economics, and performance KPIs. | PSC, Project Director, Finance, Commercial |
| Project Manager (Client) | Leads day-to-day execution; manages project team; ensures integration of engineering, procurement, and construction; reports functionally to Project Director and strategically to BOM; ensures HSSE and quality compliance. | Project Director, BOM, Functional Leads, EPC Contractor PM |
| Engineering Lead | Manages all engineering disciplines; ensures design meets codes, standards, and constructability requirements; coordinates inter-discipline reviews and approvals. | Construction Manager, QA/QC, Document Control, Contractor Engineering Team |
| HSSE Lead | Develops and implements HSSE plan; ensures compliance with regulatory and corporate HSE standards; oversees SIMOPS, toolbox talks, emergency response, and environmental protection. | Construction, Quality, Contractor HSSE Team, Regulators |
| HSSE Team (under HSSE Lead) | Conduct field audits, site safety inspections, permit-to-work verification, and incident investigation; manage safety training and reporting. | HSSE Lead, Site Supervisors |
| Quality Lead (QA/QC Lead) | Develops project quality plan; ensures inspection, testing, and documentation compliance; manages NCR/CAPA process and quality audits. | Engineering, Construction, QA/QC Inspectors, Contractor QA/QC |
| Quality Team (under QA/QC Lead) | Perform site inspections, weld/NDT verification, coating checks, and material traceability audits; maintain QA/QC records. | Quality Lead, Construction Supervisors |
| Contracts & Procurement (C&P) Lead | Develops procurement strategy; manages RFQs, bid evaluations, purchase orders, and expediting; ensures contractual compliance and supplier performance. | Project Manager, Engineering, EPC Contractor Supply Chain |
| Construction Lead | Leads site construction; manages contractors and subcontractors; ensures adherence to construction schedule, HSSE, and quality requirements; coordinates site interfaces. | Project Manager, HSSE, QA/QC, Engineering |
| Commissioning Manager | Oversees pre-commissioning and commissioning activities; coordinates system handovers, testing, and readiness for start-up; ensures commissioning deliverables are verified and accepted. | Construction, Operations, QA/QC, Vendor Representatives |
| Project Controls Lead | Manages project schedule, cost control, progress measurement, and reporting; maintains baselines and forecasts; supports change management and EVM. | Project Manager, All Functional Leads, Finance |
| Community & Local Content (LC) Lead | Manages stakeholder engagement and community relations; ensures compliance with local content requirements; implements CSR initiatives and grievance mechanisms. | Project Manager, HR, HSSE, External Affairs |
| Document Control Coordinator | Maintains EDMS; ensures proper numbering, revision, and distribution of project documents; tracks transmittals and approvals. | All Disciplines, Contractor Document Control |
| EPCC Contractor Project Manager | Single point of responsibility for engineering, procurement, construction, and commissioning; delivers project in accordance with contract; ensures HSSE, quality, schedule, and cost targets. | Client Project Manager, Contractor Discipline Leads |
| EPC Contractor Engineering Manager | Leads detailed engineering; coordinates design deliverables; manages vendor data, as-built documentation, and design clarifications. | Client Engineering Lead, Procurement, Construction |
| EPC Contractor Construction Manager | Plans and executes field construction; ensures safety, quality, and progress; manages subcontractors and site resources. | Client Construction Manager, HSSE, QA/QC |
| EPC Contractor QA/QC Manager | Implements quality control system; supervises inspections, testing, and certification; reports deviations and NCRs. | Client Quality Lead |
| EPC Contractor HSSE Manager | Oversees site safety and environmental programs; implement |  |
| Role / Position | Primary Responsibilities | Key Interfaces |
| Document Control Coordinator | Maintains EDMS; ensures proper numbering, revision, and distribution of project documents; tracks transmittals and approvals. | All Disciplines, Contractor Document Control |
| EPCC Contractor Project Manager | Single point of responsibility for engineering, procurement, construction, and commissioning; delivers project in accordance with contract; ensures HSSE, quality, schedule, and cost targets. | Client Project Manager, Contractor Discipline Leads |
| EPC Contractor Engineering Manager | Leads detailed engineering; coordinates design deliverables; manages vendor data, as-built documentation, and design clarifications. | Client Engineering Lead, Procurement, Construction |
| EPC Contractor Construction Manager | Plans and executes field construction; ensures safety, quality, and progress; manages subcontractors and site resources. | Client Construction Manager, HSSE, QA/QC |
| EPC Contractor QA/QC Manager | Implements quality control system; supervises inspections, testing, and certification; reports deviations and NCRs. | Client Quality Lead |
| EPC Contractor HSSE Manager | Oversees site safety and environmental programs; implement |  |

## 12.3 Authority Matrix (Excerpt)

| Decision | Authority |
| --- | --- |
| Technical deviation | Client Eng Manager |
| Schedule variance >10 days | Project Director |
| Cost impact >USD 250k | Client Executive Mgmt |
| Field adjustment (minor) | Construction Manager |

PART 3: (Project Controls → Contracting & Procurement Strategy → Risk → Change → Document Control → Local Content → Environmental & Sustainability → Deliverables & Close-Out → Appendices)

# Project Controls & Schedule Management Plan

## 13.1 Planning Philosophy

An integrated controls system combines Primavera P6 schedule, cost control (SAP/ledger), and risk analytics. The Master Control Schedule (MCS) is the single source of truth, with Level 1–3 breakdowns and logic ties across engineering, procurement, construction, and commissioning.

## 13.2 Baseline & Milestones (Illustrative)

| Milestone | Target | Owner |
| --- | --- | --- |
| Contract Award | Jul 2026 | Client/Contracts |
| Eng Complete (IFC) | Dec 2026 | Contractor |
| First Pipe Delivery | Feb 2027 | Procurement |
| Start Construction | Apr 2027 | Contractor |
| Mechanical Completion | Dec 2027 | Contractor |
| Commissioning Complete | Feb 2028 | PMT |

Figure 12 – High-Level Project Milestone Chart (Placeholder)

## 13.3 Progress & EVM

Weighted progress: Eng 15% / Proc 35% / Constr 40% / Comm 10%. CPI/SPI tracked monthly; variances trigger corrective action plans approved at PSC.

## 13.4 Reporting

- Weekly Dashboards: safety, progress, constraints.

- Monthly Reports: schedule/cost/risks/changes, forecast to complete (FTC).

- Quarterly Reviews: re-baseline only by PSC decision.

# Contracting & Procurement Strategy

## 14.1 Contracting Philosophy

Adopt a single EPCC LSTK to reduce interfaces and lock in schedule/cost certainty; supplement with frame agreements for inspection/specialist services.

## 14.2 Tendering & Award

Issue ITT → technical evaluation & clarifications → commercial evaluation → recommendation → negotiation → award → kick-off. Evaluation criteria balance HSSE, technical capability, past performance, local content, and price.

## 14.3 Key Contract Provisions (Illustrative)

- Performance Bond: 10%

- Advance Payment Bond: as applicable

- LDs for Delay: 0.1% per day, capped at 10% of contract price

- Early Completion Incentive: defined per day, capped

- Variation/Claims: governed under change procedure

- Dispute Resolution: amicable settlement → arbitration

## 14.4 Strategy Table

| Package | Scope | Type | Tender Method | Award Basis | Remarks |
| --- | --- | --- | --- | --- | --- |
| Main EPCC | Eng/Proc/Constr/Comm of 70 km trunkline | LSTK | Open Tender | Tech + Commercial | Single award |
| Survey/Geotech | Route/topo/soil | Unit Rate | Selective | Capability/Price | Pre-award |
| Third-Party Inspection | Vendor/site QA/QC | Call-off | Frame Agreement | Competence | On demand |
| Logistics | Transport/laydown | Service Order | Competitive | Cost/reliability | Short term |
| Insurance | CAR/EAR | Lump Sum | Negotiated | Compliance | Client arranged |

Figure 13 – Contracting Strategy Flow Diagram (Placeholder)

Narrative: The strategy hedges supply risk by early locking of long-lead items (line pipe, valves) and including expediting milestones as contractual deliverables.

# Risk Management Plan

## 15.1 Methodology

Identify, analyze, and respond to risks using a 5×5 probability/impact matrix. A consolidated register is maintained; ownership and mitigation plans are reviewed monthly, with quarterly risk workshops for deep dives.

Figure 14 – 5×5 Risk Matrix (Placeholder)

## 15.2 Sample Risk Register (Excerpt)

| ID | Risk | Cat. | Impact | Likelihood | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Delay in ROW acquisition | Schedule | High | Med | Early engagement; enable works | Client |
| R-02 | Valve late delivery | Proc | High | Med | Expediting; alt supplier options | Contractor |
| R-03 | HSE incident in trenching | HSSE | High | Low | JHA, PTW, supervision, training | Contractor |
| R-04 | Flooding/access | External | Med | Med | Sequencing to dry season; temp works | PMT |
| R-05 | FX/inflation on materials | Comm | Med | Med | Early commitment; hedging | Procurement |

## 15.3 Opportunity Management

Track positive risks (e.g., early mobilization, local vendor capacity) to capture savings and schedule gains.

# Change Management Plan

## 16.1 Process

CRF raised → impact assessment (engineering, HSSE, schedule, cost) → Change Control Board (CCB) review → approval/rejection → baseline update → Change Log update in EDMS.

Figure 15 – Change Control Workflow (Placeholder)

## 16.2 Approvals (Illustrative)

| Category | Approval |
| --- | --- |
| Technical design change | Client Eng Manager |
| Schedule variance >10 days | Project Director |
| Cost impact >USD 250k | Client Executive Mgmt |

# Document Control Plan

## 17.1 System & Numbering

All documents controlled in EDMS. Numbering format: AGT-[Discipline]-[Seq]-[Rev]. Status codes: IFR/IFC/IFU/AB. Only approved documents reach construction/commissioning.

## 17.2 Transmittals & Distribution

All issue and receipt via controlled transmittals. Acknowledgment within 48 hours. Obsolete documents are withdrawn from use.

## 17.3 Retention & Archival

Retention: 10 years post-handover (contracts 15 years). Electronic and hard-copy archives per Shark Inc. policy.

# Local Content & Community Relations Plan

## 18.1 LC Targets

≥45% local man-hours; ≥60% local procurement by value (target); local fabrication where feasible. Training and apprenticeships embedded in manpower plans.

## 18.2 Community Engagement

CLO office established; structured engagement calendar, transparent grievance mechanism (≤14-day resolution). CSR aligned with community-approved priorities.

Figure 16 – Community Engagement Meeting (Placeholder)

# Environmental & Sustainability Plan

## 19.1 Objectives

Minimize environmental footprint; comply with ESIA/permits; ensure reinstatement of ROW and crossings.

## 19.2 Controls

Erosion/sediment measures; waste segregation; hazardous materials storage; spill prevention/response; noise/dust suppression; biodiversity protection; post-construction reinstatement and tree planting.

Figure 17 – Pipeline Reinstatement & Tree Planting (Placeholder)

# Project Deliverables & Close-Out

## 20.1 Deliverables Matrix (Excerpt)

| Discipline | Deliverables | Approval |
| --- | --- | --- |
| Engineering | PFDs, P&IDs, calculations, IFCs, as-builts | Client Eng |
| Procurement | MRs, POs, ITPs, certificates, FATs | QA/QC |
| Construction | Daily reports, weld/NDT logs, hydrotest packs | Constr Mgr |
| Commissioning | Pre-Comm/Comm reports, TOPs | Client PM |
| HSSE | RA/JHA logs, incident reports, audits | HSE Mgr |
| Quality | ITPs, NCR/CAPA, dossiers | QA/QC Mgr |

## 20.2 Lessons Learned

LL captured after major phases (engineering complete, mechanical completion, commissioning). Actions feed corporate knowledge and future projects.

## 20.3 Final Handover

Turnover Packages (TOPs), spares list, training records, warranties, and as-builts delivered per handover index. Operations signoff concludes the project phase.

Figure 18 – Final Handover Ceremony (Placeholder)

# Appendices

Appendix A – Full Risk Register
Columns: ID, Description, Category, Cause, Consequence, P, I, Risk Score, Owner, Mitigation, Residual Risk, Status, Next Review.

Appendix B – Responsibility Assignment Matrix (RACI)
List deliverables vs. roles (R = Responsible, A = Accountable, C = Consulted, I = Informed).

Appendix C – Document List
Master Document Register with number, title, owner, status, revision, date, and next action.

Appendix D – Equipment & Material List
Major line items with spec, quantity, vendor, QA/ITP reference, delivery milestone, storage/preservation notes.

Appendix E – Figures & Photos
All figure placeholders to be replaced with approved images; captions retained.