WorkFlow Kits Inc.

PROJECT CHARTER

Construction of a 20km Double‑Lane Asphalt Road for Ojinga Royal Estate

Prepared by: WorkFlow Kits Inc.  •  Date: 01 October 2025  •  Version: v1.0

────────────────────────────────────────────────────────

# Revision Status

| Revision | Description | Date |
| --- | --- | --- |
| R01 | Issue for Review | 01‑Oct‑2025 |

# Approval & Sign‑Off

| Name | Title | Signature | Date |
| --- | --- | --- | --- |
| John Smith | Project Sponsor |  | 01‑Oct‑2025 |
| Chika Eze | Project Manager |  | 01‑Oct‑2025 |
| Tunde Adeyemi | Estate Committee Chair |  | 01‑Oct‑2025 |

Table of Contents

Revision Status	2

Approval & Sign‑Off	2

1. Project Overview	4

2. Purpose & Business Case	4

3. Project Scope	4

4. High‑Level Deliverables	5

5. Milestones & Timeline	5

6. Budget & Resources	5

7. Governance & Roles	6

8. Risk Management	6

9. Stakeholder Analysis	7

10. Communication Plan	7

11. Quality & Change Control	8

Appendices	8

# 1. Project Overview

Project Title: Construction of a 20km Double‑Lane Asphalt Road for Ojinga Royal Estate

Project Code / ID: WF-CR-2025-001

Project Sponsor: Engr. John Smith F(Executive Director, Infrastructure)

Project Manager: Ms. Chika Eze (Senior Project Manager)

Date Prepared: 01 October 2025

Version Control: v1.0

# 2. Purpose & Business Case

Ojinga Royal Estate is a newly developed residential community with unpaved access roads, causing travel delays, dust pollution, and increased safety risks. This project will deliver a durable, safe, and efficient 20km double‑lane asphalt road to improve accessibility and support estate growth.

Purpose: Deliver a compliant, durable road network enhancing mobility and safety.

Expected Benefits: +15% property value uplift (indicative), ~40% travel time reduction, lower life‑cycle maintenance costs, and reputation boost for WorkFlow Kits Inc.

Success Criteria: 3‑month delivery; ≤ $110,000 total cost; compliance with Nigerian Federal Highway Standards; ≥80% stakeholder satisfaction.

# 3. Project Scope

In‑Scope:

Site clearing, grading, and compaction.

Construction of a 20km dual carriageway asphalt road (approx. 7m width per lane).

Drainage infrastructure (culverts, gutters, stormwater channels).

Road markings and signage.

Street lighting infrastructure (conduits and bases; poles and luminaires excluded).

Out‑of‑Scope:

Estate perimeter fencing and landscaping.

Streetlight poles and lamp installation.

Non‑road utilities (water, power, telecom) except where directly impacted by the road works.

Assumptions:

No major utility relocations are required.

Permits are secured before mobilization.

Weather conditions will not significantly disrupt works.

Constraints:

Fixed budget of $110,000.

Strict 3‑month delivery timeline.

Seasonal labor availability constraints.

# 4. High‑Level Deliverables

| Deliverable | Description | Target Completion |
| --- | --- | --- |
| D1: Site Preparation | Clearing, grading, compacting | Week 2 |
| D2: Sub‑base & Base Course | Foundation layers placed and compacted | Week 5 |
| D3: Asphalt Paving | Lay 20km dual asphalt lanes | Week 9 |
| D4: Drainage System | Culverts, gutters, stormwater channels | Week 10 |
| D5: Road Markings & Signage | Centerlines, edge lines, crossings, signage | Week 11 |
| D6: Handover & QA Testing | Inspection, QA/QC tests, approvals | Week 12 |

# 5. Milestones & Timeline

| Milestone | Planned Date | Owner | Dependencies |
| --- | --- | --- | --- |
| Charter Approval | 01 Oct 2025 | Sponsor | None |
| Contractor Mobilization | 05 Oct 2025 | Project Manager | Approval |
| Site Preparation Complete | 15 Oct 2025 | Contractor | Mobilization |
| Asphalt Laying Complete | 30 Nov 2025 | Contractor | Sub‑base |
| QA/QC Testing | 10 Dec 2025 | Quality Lead | Paving |
| Project Handover | 31 Dec 2025 | Project Manager | QA/QC |

# 6. Budget & Resources

Estimated Budget: $110,000  •  Funding Source: Ojinga Royal Estate Developers’ Capital Budget

| Cost Item | Amount (USD) | Notes |
| --- | --- | --- |
| Earthworks & Site Prep | 20,000 | Clearing, grading, compaction |
| Asphalt & Materials | 45,000 | Bitumen, base course, aggregates |
| Equipment & Plant | 25,000 | Graders, compactors, trucks |
| Labor | 12,000 | Skilled & unskilled workforce |
| QA/QC & Testing | 3,000 | Daily density & core tests |
| Contingency (≈5%) | 5,000 | Risk reserve |

Resource Requirements:

Human Resources: Project Manager, Site Engineer (2), QA/QC Lead, HSE Officer, Surveyor, Accountant, 60 laborers.

Technology & Equipment: Asphalt paver, rollers/compactors, graders, dump trucks, survey equipment.

Facilities/Equipment: On‑site storage yard, fuel storage, temporary office cabin.

# 7. Governance & Roles

| Role | Name | Responsibility |
| --- | --- | --- |
| Sponsor | Engr. John Smith | Executive oversight, funding, decision authority |
| Project Manager | Ms. Chika Eze | Planning, execution, reporting |
| Steering Committee | Estate Committee & WF Kits PMO | Governance, escalations |
| QA/QC Lead | Mr. Ifeanyi Okoro | Quality plan, tests, acceptance |
| HSE Officer | Mrs. Amina Yusuf | HSE plan, site compliance |
| Procurement Officer | Mr. Seyi Alade | Suppliers, contracts, logistics |
| Site Engineers | Team | Daily supervision, progress tracking |

RACI Matrix:

| Task / Deliverable | R | A | C | I |
| --- | --- | --- | --- | --- |
| Requirement Gathering & Surveys | Site Engineers | PM | Sponsor | Estate Committee |
| Solution/Design Confirmation | PM | Sponsor | QA Lead | PMO |
| Sub‑base & Base Course | Contractor | PM | QA Lead | Sponsor |
| Asphalt Paving | Contractor | PM | QA Lead | Sponsor |
| QA/QC Testing | QA Lead | PM | Sponsor | Estate Committee |
| Final Handover | PM | Sponsor | Estate Committee | Residents |

# 8. Risk Management

| Risk ID | Description | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Heavy rainfall delaying paving | High | Medium | Shift scheduling; temporary covers; weather monitoring |
| R2 | Material price volatility | High | High | Early supplier lock‑in; price hedging; contingency |
| R3 | Labor shortage (festive season) | Medium | Medium | Pre‑book labor pool; incentive scheme |
| R4 | Compaction quality defects | High | Low | Daily density tests; third‑party audits; rework allowance |
| R5 | Permit/inspection delays | Medium | Low | Early engagement with regulators; submission tracker |
| R6 | Equipment breakdowns | Medium | Medium | Preventive maintenance; backup rental agreements |

# 9. Stakeholder Analysis

| Stakeholder | Role | Interest / Influence | Engagement Strategy |
| --- | --- | --- | --- |
| Estate Developers | Client & Funder | High / High | Weekly progress meetings; dashboard |
| Residents Association | End Users | High / Medium | Monthly updates; site walks |
| Local Government | Regulator | Medium / High | Permit approvals; compliance checks |
| Contractors | Delivery Agents | High / High | Daily site coordination; look‑ahead plans |
| WorkFlow Kits Inc. PMO | Oversight | Medium / Medium | Bi‑weekly reviews; risk clinics |

# 10. Communication Plan

Meeting Cadence:

Daily site huddles (Contractor, PM).

Weekly progress meetings (Sponsor, PMO, Developers).

Monthly stakeholder reviews (Developers & Residents).

Reporting & Channels:

Reports: Weekly status report; Monthly performance report; Risk register.

Tools: Project dashboard; MS Project timeline.

Channels: Email; WhatsApp project group; MS Teams; Formal letters for approvals.

Escalation Path:

Site Engineer → Project Manager → Sponsor → Steering Committee.

# 11. Quality & Change Control

Quality Standards: Nigerian Federal Highway Standards; ISO 9001 aligned QA/QC plan.

Testing: Daily compaction density tests; asphalt core sampling; drainage water tests.

Inspections: Hold points for base course, asphalt layers, and drainage structures.

Change Control: All scope/schedule/budget changes require Sponsor & Steering Committee approval; log in Change Register; update baseline and communicate to all stakeholders.

# Appendices

Appendix A: Acronyms & Definitions

Appendix B: Reference to Nigerian Road Construction Standards

Appendix C: Preliminary Cost Estimate Breakdown

Appendix D: Risk Register (Detailed)